## Dashboard
Hera UAT — Test Execution Dashboard
Source: Hera_UAT_Test_Plan_20260910-153936.xlsx
Generated: 2026-09-11 10:11
Total test cases |  | Executed so far |  | Passed |  | Failed |  | Not started yet | Pass rate — among tests executed so far
196 |  | 65 (33% of total) |  | 49 |  | 16 |  | 131 | 75%
Overall status
Status | Count
Passed | 49
Failed | 15
Error | 1
Inconclusive | 0
Skipped | 0
Not started | 131
By process
Process | Total | Passed | Failed | Error | Inconclusive | Skipped | Not started | Pass rate
ACS | 38 | 4 | 0 | 0 | 0 | 0 | 34 | 100%
Bay Occupancy | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0%
Bidding module | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0%
HERA access & authorization | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0%
Invoicing | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0%
NCC | 14 | 0 | 0 | 0 | 0 | 0 | 14 | 0%
Nominations | 57 | 38 | 11 | 1 | 0 | 0 | 7 | 76%
Planned maintenance | 13 | 1 | 4 | 0 | 0 | 0 | 8 | 20%
Plant communication | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0%
Plant monitoring | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0%
Profiles | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0%
Profiles - Optimizer | 9 | 0 | 0 | 0 | 0 | 0 | 9 | 0%
Profiles - override | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0%
Scheduled Transfers | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0%
Scheduler | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 100%
Test data preparation | 20 | 0 | 0 | 0 | 0 | 0 | 20 | 0%

## By Process & Subprocess
Process | Subprocess | Total | Passed | Failed | Error | Inconclusive | Skipped | Not started | Pass rate
ACS | Master data | 3 | 2 | 0 | 0 | 0 | 0 | 1 | 100%
ACS | Master data – Driver | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0%
ACS | Master data – Qualification workflow | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0%
ACS | Master data – Trailer | 5 | 2 | 0 | 0 | 0 | 0 | 3 | 100%
ACS | Master data – Transport company | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0%
ACS | Master data – Truck | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0%
ACS | Validation | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0%
ACS | eCMR | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0%
ACS — Total |  | 38 | 4 | 0 | 0 | 0 | 0 | 34 | 100%
Bay Occupancy | Occupancy screen | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0%
Bay Occupancy — Total |  | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0%
Bidding module | Sending bids | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0%
Bidding module | Utilities electricity consumption | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0%
Bidding module — Total |  | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0%
HERA access & authorization | authorization | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0%
HERA access & authorization — Total |  | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0%
Invoicing | Outgoing invoices | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0%
Invoicing | Receiving invoices | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0%
Invoicing — Total |  | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0%
NCC | Actual | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0%
NCC | Costs Breakdown UI | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0%
NCC | Forecast | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0%
NCC | Forecast – calculation validation | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0%
NCC | Forecast € calculation validation | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0%
NCC — Total |  | 14 | 0 | 0 | 0 | 0 | 0 | 14 | 0%
Nominations | Additional nomination | 7 | 2 | 1 | 0 | 0 | 0 | 4 | 66.67%
Nominations | Weekly nomination | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 80%
Nominations | Weekly nomination – UI | 14 | 13 | 1 | 0 | 0 | 0 | 0 | 92.86%
Nominations | Weekly nomination – invalid CSV | 11 | 7 | 4 | 0 | 0 | 0 | 0 | 63.64%
Nominations | Yearly nomination | 7 | 5 | 0 | 1 | 0 | 0 | 1 | 83.33%
Nominations | Yearly nomination – invalid CSV | 13 | 7 | 4 | 0 | 0 | 0 | 2 | 63.64%
Nominations — Total |  | 57 | 38 | 11 | 1 | 0 | 0 | 7 | 76%
Planned maintenance | Creation | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0%
Planned maintenance | Delete | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0%
Planned maintenance | Edit | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0%
Planned maintenance | End-to-end profile compliance | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0%
Planned maintenance | Profile curve impact | 4 | 1 | 3 | 0 | 0 | 0 | 0 | 25%
Planned maintenance — Total |  | 13 | 1 | 4 | 0 | 0 | 0 | 8 | 20%
Plant communication | Receiving data | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0%
Plant communication | Sending data | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0%
Plant communication — Total |  | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0%
Plant monitoring | Component status | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0%
Plant monitoring | Plant capacity | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0%
Plant monitoring | Plant connection | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0%
Plant monitoring — Total |  | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0%
Profiles | Profiles screen | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0%
Profiles — Total |  | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0%
Profiles - Optimizer | Fast filling – full power | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0%
Profiles - Optimizer | Hera vs Plant SIM | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0%
Profiles - Optimizer | Integration output | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0%
Profiles - Optimizer | Logic control optimal | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0%
Profiles - Optimizer | Manual fast loading – half power | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0%
Profiles - Optimizer — Total |  | 9 | 0 | 0 | 0 | 0 | 0 | 9 | 0%
Profiles - override | Creation | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0%
Profiles - override | Integration output | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0%
Profiles - override — Total |  | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0%
Scheduled Transfers | Profiles & occupancy – filling validation | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0%
Scheduled Transfers | Profiles & occupancy – rejection impact | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0%
Scheduled Transfers | Profiles & occupancy – session capture | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0%
Scheduled Transfers | Profiles & occupancy – status filter | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0%
Scheduled Transfers — Total |  | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0%
Scheduler | Slot confirmation | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 100%
Scheduler | Slot rejection | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 100%
Scheduler — Total |  | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 100%
Test data preparation | CSV Generator – ApplyPowerConstraints | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0%
Test data preparation | CSV Generator – BuildNominations | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0%
Test data preparation | CSV Generator – DST | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0%
Test data preparation | CSV Generator – Export | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0%
Test data preparation | CSV Generator – Parity | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0%
Test data preparation | CSV Generator – Yearly | 13 | 0 | 0 | 0 | 0 | 0 | 13 | 0%
Test data preparation — Total |  | 20 | 0 | 0 | 0 | 0 | 0 | 20 | 0%
GRAND TOTAL |  | 196 | 49 | 15 | 1 | 0 | 0 | 131 | 75.38%

## Details
Process | Subprocess | Test case ID | Title | Coverage | Status | Tester | Comment
ACS | Master data | ACS_MD_09 | Registry transport company list view | Automated | Passed | LucaParraGabarron | [2026-09-10 17:17 – test_master_data.py]
ACS | Master data | ACS_MD_10 | Visualisation – drivers, trucks, trailers lists | Not yet automated | Passed | LucaParraGabarron | [2026-09-10 17:17 – test_master_data.py]
ACS | Master data | ACS_MD_11 | Compare qualified entities with ACS database | Not yet automated | Not started
ACS | Master data – Driver | ACS_MD_05 | Add new driver as Pre-Qualified (happy path) | Automated | Not started
ACS | Master data – Driver | ACS_MD_06 | Promote driver Pre-Qualified → Qualified (edit) | Automated | Not started
ACS | Master data – Driver | ACS_TM_DRV_01 | Badge ID wrong format or length | Automated | Not started
ACS | Master data – Driver | ACS_TM_DRV_02 | Invalid or empty ADR Card Number | Automated | Not started
ACS | Master data – Driver | ACS_TM_DRV_03 | Empty last name or first name | Automated | Not started
ACS | Master data – Driver | ACS_TM_DRV_04 | Save without transport company | Automated | Not started
ACS | Master data – Qualification workflow | ACS_TM_QUAL_01 | Truck – attempt to create as Qualified → save blocked | Automated | Not started
ACS | Master data – Qualification workflow | ACS_TM_QUAL_02 | Trailer – attempt to create as Qualified → save blocked | Automated | Not started
ACS | Master data – Qualification workflow | ACS_TM_QUAL_03 | Driver – attempt to create as Qualified → save blocked | Automated | Not started
ACS | Master data – Qualification workflow | ACS_TM_QUAL_04 | Truck – promote to Qualified without qualification date | Automated | Not started
ACS | Master data – Qualification workflow | ACS_TM_QUAL_05 | Driver – promote to Qualified without Last Validated Training date | Automated | Not started
ACS | Master data – Trailer | ACS_MD_07 | Add new trailer as Pre-Qualified (happy path) | Automated | Not started
ACS | Master data – Trailer | ACS_MD_08 | Promote trailer Pre-Qualified → Qualified (edit) | Automated | Not started
ACS | Master data – Trailer | ACS_TM_TRL_01 | License plate invalid for country B | Automated | Not started
ACS | Master data – Trailer | ACS_TM_TRL_02 | Invalid Global Max Flow Rate | Automated | Passed | LucaParraGabarron | [2026-09-10 17:17 – test_master_data.py]
ACS | Master data – Trailer | ACS_TM_TRL_03 | Save without trailer type or offtaker company | Automated | Passed | LucaParraGabarron | [2026-09-10 17:17 – test_master_data.py]
ACS | Master data – Transport company | ACS_MD_01 | Add new transport company (happy path) | Automated | Not started
ACS | Master data – Transport company | ACS_MD_02 | Edit transport company | Automated | Not started
ACS | Master data – Transport company | ACS_TM_CO_01 | Invalid VAT number format | Automated | Not started
ACS | Master data – Transport company | ACS_TM_CO_02 | Save company without offtaker mapping (allowed) | Automated | Not started
ACS | Master data – Transport company | ACS_TM_CO_03 | Empty company name | Automated | Not started
ACS | Master data – Truck | ACS_MD_03 | Add new truck as Pre-Qualified (happy path) | Automated | Not started
ACS | Master data – Truck | ACS_MD_04 | Promote truck Pre-Qualified → Qualified (edit) | Automated | Not started
ACS | Master data – Truck | ACS_TM_TRK_01 | License plate not valid for country B | Automated | Not started |  | Also try: plate with dashes 1-ABC-123 vs compact 2ABY123.
ACS | Master data – Truck | ACS_TM_TRK_02 | Country code mismatch with license plate | Automated | Not started
ACS | Master data – Truck | ACS_TM_TRK_03 | Empty license plate | Automated | Not started
ACS | Master data – Truck | ACS_TM_TRK_04 | Duplicate license plate | Automated | Not started
ACS | Master data – Truck | ACS_TM_TRK_05 | Save without transport company selected | Automated | Not started
ACS | Master data – Truck | ACS_TM_TRK_06 | Promote to Qualified with qualification date cleared → blocked | Automated | Not started
ACS | Validation | ACS_VAL_01 | Valid entry – truck, trailer, driver | Not yet automated | Not started
ACS | Validation | ACS_VAL_02 | Non-valid entry – wrong truck or driver | Not yet automated | Not started
ACS | Validation | ACS_VAL_03 | Gate opening on valid signal | Not yet automated | Not started
ACS | Validation | ACS_VAL_04 | Exit blocked until eCMR completed | Not yet automated | Not started
ACS | eCMR | ACS_ECMR_01 | eCMR matching | Not yet automated | Not started
ACS | eCMR | ACS_ECMR_02 | eCMR data append – filling quantities | Not yet automated | Not started
Bay Occupancy | Occupancy screen | OCC_01 | Baseline bay occupancy after import | Not yet automated | Not started
Bay Occupancy | Occupancy screen | OCC_02 | Bay occupancy after confirmation | Automated | Not started
Bay Occupancy | Occupancy screen | OCC_03 | Bay occupancy after rejection | Automated | Not started
Bay Occupancy | Occupancy screen | OCC_04 | Bay occupancy with maintenance + Confirm Week | Not yet automated | Not started
Bay Occupancy | Occupancy screen | OCC_05 | Book every slot respecting maintenance | Not yet automated | Not started
Bidding module | Sending bids | BID_02 | BRP electricity DA bid | Not yet automated | Not started
Bidding module | Sending bids | BID_03 | BRP gas DA bid | Not yet automated | Not started
Bidding module | Sending bids | BID_04 | BSP DA bid (aFRR) | Not yet automated | Not started
Bidding module | Utilities electricity consumption | BID_01 | Derive total plant electricity from electrolyser profile | Not yet automated | Not started
HERA access & authorization | authorization | AUTH_01 | Create a new valid account | Not yet automated | Not started
HERA access & authorization | authorization | AUTH_02 | Login with authorized account | Not yet automated | Not started
HERA access & authorization | authorization | AUTH_03 | Login with unauthorized account | Not yet automated | Not started
HERA access & authorization | authorization | AUTH_04 | Verify IP control (if enabled) | Not yet automated | Not started
Invoicing | Outgoing invoices | INV_02 | Generate outgoing invoice from NCC/offtake | Not yet automated | Not started
Invoicing | Receiving invoices | INV_01 | Exact Online data fetching | Not yet automated | Not started
NCC | Actual | NCC_ACT_01 | Actual NCC creation (post-operation) | Not yet automated | Not started
NCC | Costs Breakdown UI | NCC_UI_01 | Costs Breakdown page loads — 3 NCC Forecast cards visible | Automated | Not started
NCC | Costs Breakdown UI | NCC_UI_02 | 7-day navigation cycle — every day triggers fresh API data | Automated | Not started
NCC | Costs Breakdown UI | NCC_UI_03 | Costs breakdown after confirmation | Not yet automated | Not started
NCC | Costs Breakdown UI | NCC_UI_04 | Costs breakdown after rejection | Not yet automated | Not started
NCC | Costs Breakdown UI | NCC_UI_05 | €/MWh ↔ €/kg unit toggle — no errors, display updates | Automated | Not started
NCC | Forecast | NCC_UI_06 | NCC visualisation on UI | Not yet automated | Not started
NCC | Forecast – calculation validation | NCC_CALC_01 | NCC when no slots booked | Not yet automated | Not started
NCC | Forecast – calculation validation | NCC_CALC_02 | NCC when only one offtaker has pickups | Not yet automated | Not started
NCC | Forecast – calculation validation | NCC_CALC_03 | NCC when both offtakers book | Not yet automated | Not started
NCC | Forecast – calculation validation | NCC_CALC_04 | NCC with positive electricity/gas price spread | Not yet automated | Not started
NCC | Forecast – calculation validation | NCC_CALC_05 | NCC with negative price spread | Not yet automated | Not started
NCC | Forecast – calculation validation | NCC_CALC_06 | Trailer-to-offtaker allocation in NCC | Not yet automated | Not started
NCC | Forecast € calculation validation | NCC_CALC_07 | Daily NCC Python vs API: ¦diff¦ < 0.02 €/kg or ¦pct¦ < 1 % — all 7 days | Automated | Not started
Nominations | Additional nomination | Nom_AN_01 | Create slot via UI (happy path) | Automated | Not started
Nominations | Additional nomination | Nom_AN_02 | Create slot with inconsistent trailer types | Automated | Passed | LucaParraGabarron | [2026-09-10 16:24 – test_weekly_ui.py]
Nominations | Additional nomination | Nom_AN_03 | Create slot with inconsistent transfers (two drops without pick-up) | Automated | Failed | LucaParraGabarron | [2026-09-10 16:24 – test_weekly_ui.py] Possible to have 2 consecutives drop off
Nominations | Additional nomination | Nom_AN_04 | Delete one transfer from slot | Automated | Not started
Nominations | Additional nomination | Nom_AN_05 | Delete slot entirely | Automated | Passed | LucaParraGabarron | [2026-09-10 16:24 – test_weekly_ui.py]
Nominations | Additional nomination | Nom_AN_06 | Modify slot – change offtaker | Automated | Not started
Nominations | Additional nomination | Nom_AN_07 | Modify slot – change trailer type | Automated | Not started
Nominations | Weekly nomination | Nom_WN_01 | Upload correct weekly nomination of offtaker | Automated | Passed | LucaParraGabarron | [2026-09-10 16:04 – test_weekly_import.py]
Nominations | Weekly nomination | Nom_WN_03 | Import CSV for second offtaker same week | Automated | Passed | LucaParraGabarron | [2026-09-10 16:04 – test_weekly_import.py]
Nominations | Weekly nomination | Nom_WN_04 | Overwrite weekly nomination before deadline | Automated | Passed | LucaParraGabarron | [2026-09-10 16:04 – test_weekly_import.py]
Nominations | Weekly nomination | Nom_WN_05 | Overwrite weekly nomination after deadline | Automated | Failed | LucaParraGabarron | [2026-09-10 16:04 – test_weekly_import.py] It should not be possible to import in the past
Nominations | Weekly nomination | Nom_WN_08 | Visual check – transfers created with New status after import | Automated | Passed | LucaParraGabarron | [2026-09-10 16:04 – test_weekly_import.py]
Nominations | Weekly nomination – UI | Nom_WN_UI_01 | View Week 21/2027 scheduling grid – verify NEW slots (UI_01) | Automated | Passed | LucaParraGabarron | [2026-09-10 16:24 – test_weekly_ui.py]
Nominations | Weekly nomination – UI | Nom_WN_UI_02 | Change offtaker in slot modal and verify persistence (UI_02) | Automated | Failed | LucaParraGabarron | [2026-09-10 16:24 – test_weekly_ui.py] Changinf the offtaker of a scheduled transfer does not work
Nominations | Weekly nomination – UI | Nom_WN_UI_03 | Change trailer type in slot modal and verify persistence (UI_03) | Automated | Passed | LucaParraGabarron | [2026-09-10 16:24 – test_weekly_ui.py]
Nominations | Weekly nomination – UI | Nom_WN_UI_04 | Add a trailer row in slot modal and verify persistence (UI_04) | Automated | Passed | LucaParraGabarron | [2026-09-10 16:24 – test_weekly_ui.py]
Nominations | Weekly nomination – UI | Nom_WN_UI_05 | Delete a trailer row in slot modal and verify persistence (UI_05) | Automated | Passed | LucaParraGabarron | [2026-09-10 16:24 – test_weekly_ui.py]
Nominations | Weekly nomination – UI | Nom_WN_UI_06 | Confirm an individual NEW slot (UI_06) | Automated | Passed | LucaParraGabarron | [2026-09-10 16:24 – test_weekly_ui.py]
Nominations | Weekly nomination – UI | Nom_WN_UI_07 | Reject the individually confirmed slot (UI_07) | Automated | Passed | LucaParraGabarron | [2026-09-10 16:24 – test_weekly_ui.py]
Nominations | Weekly nomination – UI | Nom_WN_UI_08 | Confirm all remaining NEW slots individually (UI_08) | Automated | Passed | LucaParraGabarron | [2026-09-10 16:24 – test_weekly_ui.py]
Nominations | Weekly nomination – UI | Nom_WN_UI_09 | Reject all filled slots individually (UI_09) | Automated | Passed | LucaParraGabarron | [2026-09-10 16:24 – test_weekly_ui.py]
Nominations | Weekly nomination – UI | Nom_WN_UI_10 | Bulk confirm entire week via ‘Confirm Week’ button (UI_10) | Automated | Passed | LucaParraGabarron | [2026-09-10 16:24 – test_weekly_ui.py]
Nominations | Weekly nomination – UI | Nom_WN_UI_11 | Bulk reject entire week via ‘Confirm Week’ button (UI_11) | Automated | Passed | LucaParraGabarron | [2026-09-10 16:24 – test_weekly_ui.py]
Nominations | Weekly nomination – UI | Nom_WN_UI_12 | Add a new Virya slot via UI on an empty calendar cell (UI_12) | Automated | Passed | LucaParraGabarron | [2026-09-10 16:24 – test_weekly_ui.py]
Nominations | Weekly nomination – UI | Nom_WN_UI_SETUP_01 | Set up Week 21/2027 – import Virya baseline (SETUP_01) | Automated | Passed | LucaParraGabarron | [2026-09-10 16:24 – test_weekly_ui.py]
Nominations | Weekly nomination – UI | Nom_WN_UI_SETUP_02 | Set up Week 21/2027 – re-import baseline for bulk tests (SETUP_02) | Automated | Passed | LucaParraGabarron | [2026-09-10 16:24 – test_weekly_ui.py]
Nominations | Weekly nomination – invalid CSV | Nom_WN_NEG_03 | Slot start/end times modified after export | Automated | Passed | LucaParraGabarron | [2026-09-10 16:04 – test_weekly_import.py]
Nominations | Weekly nomination – invalid CSV | Nom_WN_NEG_05 | Trailer booked on wrong-parity slot (grey slot tampering) | Automated | Failed | LucaParraGabarron | [2026-09-10 16:04 – test_weekly_import.py] 2 trailer are being dropped off during the same pickupslot 1 from messer and 1 from virya
Nominations | Weekly nomination – invalid CSV | Nom_WN_NEG_06 | Invalid trailer type name | Automated | Passed | LucaParraGabarron | [2026-09-10 16:04 – test_weekly_import.py]
Nominations | Weekly nomination – invalid CSV | Nom_WN_NEG_07 | Wrong or missing column headers | Automated | Passed | LucaParraGabarron | [2026-09-10 16:04 – test_weekly_import.py]
Nominations | Weekly nomination – invalid CSV | Nom_WN_NEG_08 | Maint. row with trailer data pasted in CSV | Automated | Failed | LucaParraGabarron | [2026-09-10 16:04 – test_weekly_import.py] 1. there are 2 succeding slots picked by the same offtaker. 2.ASlot can be picked even if the maintenance does not allow it
Nominations | Weekly nomination – invalid CSV | Nom_WN_NEG_10 | Overlapping slot times (edited End into next slot) | Automated | Passed | LucaParraGabarron | [2026-09-10 16:04 – test_weekly_import.py]
Nominations | Weekly nomination – invalid CSV | Nom_WN_NEG_13 | Wrong date format in CSV | Automated | Passed | LucaParraGabarron | [2026-09-10 16:04 – test_weekly_import.py]
Nominations | Weekly nomination – invalid CSV | Nom_WN_NEG_15 | Second Drop-Off before first trailer is picked up (plant occupied) | Automated | Failed | LucaParraGabarron | [2026-09-10 16:04 – test_weekly_import.py] Capable of picking 2 successive drop-off : 2 trailers of the same offtaker planned to be on site at the same time
Nominations | Weekly nomination – invalid CSV | Nom_WN_NEG_16 | Values changed between generator export and Hera import (within limits) | Automated | Passed | LucaParraGabarron | [2026-09-10 16:04 – test_weekly_import.py] Normal because only 1 trailer type
Nominations | Weekly nomination – invalid CSV | Nom_WN_NEG_17 | Pick-Up when no trailer at plant (empty plant) | Automated | Failed | LucaParraGabarron | [2026-09-10 16:04 – test_weekly_import.py] A pick up has been planned but no prior drop-off, normally impossible
Nominations | Weekly nomination – invalid CSV | Nom_WN_NEG_18 | Pick-Up trailer type does not match previously dropped trailer type | Automated | Passed | LucaParraGabarron | [2026-09-10 16:04 – test_weekly_import.py]
Nominations | Yearly nomination | Nom_YN_01 | Upload correct yearly nomination of offtaker | Automated | Error | LucaParraGabarron | [2026-09-10 17:07 – test_yearly_import.py] Page.goto: Navigation to "https://herawebtest.azurewebsites.net/nominations/yearly" is interrupted by another navigation to "https://login.microsoftonline.com/f48f023f-f1f2-4a42-92aa-bebb215f31d0/login" Call log: - navigating to "https://herawebtest.azurewebsites.net/nominations/yearly", waiting until "domcontentloaded"
Nominations | Yearly nomination | Nom_YN_02 | Upload wrongly formatted yearly nomination | Not yet automated | Not started
Nominations | Yearly nomination | Nom_YN_03 | Happy path – Messer Year 2028 (second offtaker import) | Automated | Passed | LucaParraGabarron | [2026-09-10 17:07 – test_yearly_import.py]
Nominations | Yearly nomination | Nom_YN_04 | Second import overwrites – Virya Year 2028 V2 (170/month, 38/week) | Automated | Passed | LucaParraGabarron | [2026-09-10 17:07 – test_yearly_import.py]
Nominations | Yearly nomination | Nom_YN_05 | Access/view uploaded yearly nomination | Automated | Passed | LucaParraGabarron | [2026-09-10 17:13 – test_yearly_ui.py]
Nominations | Yearly nomination | Nom_YN_06 | Edit history breakdown and submit new version | Automated | Passed | LucaParraGabarron | [2026-09-10 17:13 – test_yearly_ui.py]
Nominations | Yearly nomination | Nom_YN_07 | Yearly chart view | Automated | Passed | LucaParraGabarron | [2026-09-10 17:13 – test_yearly_ui.py]
Nominations | Yearly nomination – invalid CSV | Nom_YN_NEG_01 | Wrong offtaker selected at import (file vs modal) | Not yet automated | Not started
Nominations | Yearly nomination – invalid CSV | Nom_YN_NEG_02 | Year mismatch between CSV filename and Hera year selector | Not yet automated | Not started
Nominations | Yearly nomination – invalid CSV | Nom_YN_NEG_03 | Month trailer count exceeds AllowedPerMonth (tampered CSV) | Automated | Failed | LucaParraGabarron | [2026-09-10 17:07 – test_yearly_import.py] Hera is not aware of the monthly cap and accept value above
Nominations | Yearly nomination – invalid CSV | Nom_YN_NEG_04 | Week trailer count exceeds AllowedPerWeek (tampered CSV) | Automated | Failed | LucaParraGabarron | [2026-09-10 17:07 – test_yearly_import.py] Hera ignore the weekly cap
Nominations | Yearly nomination – invalid CSV | Nom_YN_NEG_05 | Negative trailer count in CSV | Automated | Passed | LucaParraGabarron | [2026-09-10 17:07 – test_yearly_import.py]
Nominations | Yearly nomination – invalid CSV | Nom_YN_NEG_06 | Non-integer trailer count (decimal or text) | Automated | Passed | LucaParraGabarron | [2026-09-10 17:07 – test_yearly_import.py]
Nominations | Yearly nomination – invalid CSV | Nom_YN_NEG_07 | Missing month row(s) in CSV | Automated | Failed | LucaParraGabarron | [2026-09-10 17:07 – test_yearly_import.py] There is no warning to say that a month was missing in the CSV uploaded
Nominations | Yearly nomination – invalid CSV | Nom_YN_NEG_08 | Missing ISO week row(s) in CSV | Automated | Failed | LucaParraGabarron | [2026-09-10 17:07 – test_yearly_import.py] There was no warning to say that a week was missing from the csv
Nominations | Yearly nomination – invalid CSV | Nom_YN_NEG_09 | Invalid Type value in CSV | Automated | Passed | LucaParraGabarron | [2026-09-10 17:07 – test_yearly_import.py]
Nominations | Yearly nomination – invalid CSV | Nom_YN_NEG_10 | Invalid Period value (out of range) | Automated | Passed | LucaParraGabarron | [2026-09-10 17:07 – test_yearly_import.py]
Nominations | Yearly nomination – invalid CSV | Nom_YN_NEG_12 | Empty CSV or header-only file | Automated | Passed | LucaParraGabarron | [2026-09-10 17:07 – test_yearly_import.py]
Nominations | Yearly nomination – invalid CSV | Nom_YN_NEG_14 | Duplicate Period entries in CSV | Automated | Passed | LucaParraGabarron | [2026-09-10 17:07 – test_yearly_import.py]
Nominations | Yearly nomination – invalid CSV | Nom_YN_NEG_15 | Wrong column headers (typo or reorder) | Automated | Passed | LucaParraGabarron | [2026-09-10 17:07 – test_yearly_import.py]
Planned maintenance | Creation | MAINT_CR_01 | Create short maintenance block (~2 h) in the future | Automated | Not started
Planned maintenance | Creation | MAINT_CR_02 | Create long maintenance block spanning 3 days | Automated | Not started
Planned maintenance | Creation | MAINT_CR_03 | Attempt to create maintenance in the past -> error expected | Automated | Not started
Planned maintenance | Delete | MAINT_DEL_01 | Delete maintenance block via trash icon in edit dialog | Automated | Failed | LucaParraGabarron | [2026-09-10 17:21 – test_planned_maintenance.py] s
Planned maintenance | Edit | MAINT_ED_01 | Edit maintenance block - change asset and verify persistence | Automated | Not started
Planned maintenance | Edit | MAINT_ED_02 | Edit maintenance block - extend end date to further future and verify persistence | Automated | Not started
Planned maintenance | Edit | MAINT_ED_03 | Edit maintenance block - set end date to the past -> error expected | Automated | Not started
Planned maintenance | End-to-end profile compliance | E2E_MAINT_01 | Power consumption <= nominal capacity across full week (HPC Tuesday, Stack Thursday) | Automated | Not started
Planned maintenance | End-to-end profile compliance | E2E_MAINT_02 | Loading Bay 1 in maintenance full week -> Truck Filling curve = 0 at every timestamp | Automated | Not started
Planned maintenance | Profile curve impact | MAINT_PR_01 | Electrolyser Stack in maintenance -> nominal capacity = 0 kW in profile | Automated | Failed | LucaParraGabarron | [2026-09-10 17:21 – test_planned_maintenance.py]
Planned maintenance | Profile curve impact | MAINT_PR_02 | High Pressure Compressor in maintenance -> nominal capacity = 12 500 kW | Automated | Failed | LucaParraGabarron | [2026-09-10 17:21 – test_planned_maintenance.py]
Planned maintenance | Profile curve impact | MAINT_PR_03 | Low Pressure Compressor in maintenance -> nominal capacity = 12 500 kW | Automated | Failed | LucaParraGabarron | [2026-09-10 17:21 – test_planned_maintenance.py]
Planned maintenance | Profile curve impact | MAINT_PR_04 | No maintenance in window -> nominal capacity = 25 000 kW (baseline sanity check) | Automated | Passed | LucaParraGabarron | [2026-09-10 17:21 – test_planned_maintenance.py]
Plant communication | Receiving data | PLANT_COM_03 | Receive actual electrolyser consumption | Not yet automated | Not started
Plant communication | Receiving data | PLANT_COM_04 | Receive actual metered data | Not yet automated | Not started
Plant communication | Sending data | PLANT_COM_01 | Send profile setpoint to plant | Not yet automated | Not started
Plant communication | Sending data | PLANT_COM_02 | Send ACS information to plant/gate | Not yet automated | Not started
Plant monitoring | Component status | PLANT_MON_04 | Visualise individual component health | Not yet automated | Not started
Plant monitoring | Plant capacity | PLANT_MON_01 | Visualise plant capacity – current state | Not yet automated | Not started
Plant monitoring | Plant capacity | PLANT_MON_02 | Visualise plant capacity – future with maintenance | Not yet automated | Not started
Plant monitoring | Plant connection | PLANT_MON_03 | Visualise plant–server connection status | Not yet automated | Not started
Profiles | Profiles screen | PROF_01 | Baseline profiles after import (no confirm) | Not yet automated | Not started
Profiles | Profiles screen | PROF_02 | Profiles after slot confirmation | Automated | Not started
Profiles | Profiles screen | PROF_03 | Profiles after slot rejection | Automated | Not started
Profiles | Profiles screen | PROF_04 | Profiles after maintenance + Confirm Week | Not yet automated | Not started
Profiles | Profiles screen | PROF_05 | MW / g/s unit toggle | Not yet automated | Not started
Profiles | Profiles screen | PROF_06 | Week navigation on Profiles | Not yet automated | Not started
Profiles - Optimizer | Fast filling – full power | PROF_FF_01 | Fast filling trapezoid profile at maxflow (slot n drop-off, n+2 pick-up, no maintenance) | Not yet automated | Not started
Profiles - Optimizer | Hera vs Plant SIM | PROF_OPT_01 | Compare Power consumption (MW) with Plant SIM ELY setpoint | Not yet automated | Not started
Profiles - Optimizer | Hera vs Plant SIM | PROF_OPT_02 | Compare Loading Bay flows (g/s) with Plant SIM DI1–DI4 | Not yet automated | Not started
Profiles - Optimizer | Hera vs Plant SIM | PROF_OPT_03 | Profile comparison on maintenance day | Not yet automated | Not started
Profiles - Optimizer | Hera vs Plant SIM | PROF_OPT_04 | Profile comparison – dev vs test environment | Not yet automated | Not started
Profiles - Optimizer | Integration output | PROF_OPT_08 | Profiles sent to Plant SIM match Hera Profiles screen | Not yet automated | Not started
Profiles - Optimizer | Logic control optimal | PROF_OPT_05 | Optimizer output – single offtaker full week | Not yet automated | Not started
Profiles - Optimizer | Logic control optimal | PROF_OPT_06 | Optimizer output – both offtakers alternating | Not yet automated | Not started
Profiles - Optimizer | Manual fast loading – half power | PROF_OPT_07 | Manual fast loading trapezoid under half-power maintenance (slot n drop-off, n+4 pick-up) | Not yet automated | Not started
Profiles - override | Creation | PROF_OVR_01 | Create manual profile override | Not yet automated | Not started
Profiles - override | Integration output | PROF_OVR_02 | Override sent to plant instead of optimized profile | Not yet automated | Not started
Scheduled Transfers | Profiles & occupancy – filling validation | SCHED_TRF_02 | Profiles + Bay Occupancy (week+1) – validate filling segments vs loading sessions | Automated | Not started
Scheduled Transfers | Profiles & occupancy – filling validation | SCHED_TRF_03 | Count: loading sessions == filling segments | Automated | Not started
Scheduled Transfers | Profiles & occupancy – filling validation | SCHED_TRF_04 | ManualFastLoading limits per filling segment | Automated | Not started
Scheduled Transfers | Profiles & occupancy – filling validation | SCHED_TRF_05 | Profiles ↔ Bay Occupancy alignment – Filling occupation per bay | Automated | Not started
Scheduled Transfers | Profiles & occupancy – filling validation | SCHED_TRF_06 | Bay Occupancy derivation – Drop/Filling/Pick from loading sessions | Automated | Not started
Scheduled Transfers | Profiles & occupancy – rejection impact | SCHED_TRF_08 | Reject all confirmed slots → profiles & bay occupancy clear to zero | Automated | Not started
Scheduled Transfers | Profiles & occupancy – session capture | SCHED_TRF_01 | Capture scheduling screen (week+1) – identify loading sessions | Automated | Not started
Scheduled Transfers | Profiles & occupancy – status filter | SCHED_TRF_07 | NEW & REJECTED transfers must not appear in profiles or bay occupancy | Automated | Not started
Scheduler | Slot confirmation | SCHED_CONF_01 | Confirm single NEW slot (modal) | Automated | Passed | LucaParraGabarron | [2026-09-10 16:24 – test_weekly_ui.py]
Scheduler | Slot confirmation | SCHED_CONF_02 | Confirm all NEW slots one by one | Automated | Passed | LucaParraGabarron | [2026-09-10 16:24 – test_weekly_ui.py]
Scheduler | Slot confirmation | SCHED_CONF_03 | Confirm Week (bulk) | Automated | Passed | LucaParraGabarron | [2026-09-10 16:24 – test_weekly_ui.py]
Scheduler | Slot rejection | SCHED_REJ_01 | Reject single confirmed slot | Automated | Passed | LucaParraGabarron | [2026-09-10 16:24 – test_weekly_ui.py]
Scheduler | Slot rejection | SCHED_REJ_02 | Reject all confirmed slots one by one | Automated | Passed | LucaParraGabarron | [2026-09-10 16:24 – test_weekly_ui.py]
Scheduler | Slot rejection | SCHED_REJ_03 | Reject Week (bulk) | Automated | Passed | LucaParraGabarron | [2026-09-10 16:24 – test_weekly_ui.py]
Test data preparation | CSV Generator – ApplyPowerConstraints | CSV_GEN_03 | Apply half-power constraints (=12500 kW) | Manual process | Not started
Test data preparation | CSV Generator – ApplyPowerConstraints | CSV_GEN_04 | Apply zero-power constraints | Manual process | Not started
Test data preparation | CSV Generator – ApplyPowerConstraints | CSV_GEN_05 | Apply full power (Pmax 25000 kW) – no constraints | Manual process | Not started
Test data preparation | CSV Generator – BuildNominations | CSV_GEN_01 | Generate weekly nomination template (slots + power data) | Manual process | Not started
Test data preparation | CSV Generator – DST | CSV_GEN_09 | Slot times correct across DST spring-forward week | Manual process | Not started
Test data preparation | CSV Generator – Export | CSV_GEN_06 | Export weekly nomination CSV | Manual process | Not started
Test data preparation | CSV Generator – Parity | CSV_GEN_02 | Verify offtaker slot alternation (Virya vs Messer parity) | Manual process | Not started
Test data preparation | CSV Generator – Yearly | CSV_GEN_Y01 | Generate yearly nomination template (months + ISO weeks) | Manual process | Not started
Test data preparation | CSV Generator – Yearly | CSV_GEN_Y02 | Verify per-offtaker trailer limits (Lists sheet) | Manual process | Not started
Test data preparation | CSV Generator – Yearly | CSV_GEN_Y03 | Month trailer count validation (0 to AllowedPerMonth) | Manual process | Not started
Test data preparation | CSV Generator – Yearly | CSV_GEN_Y04 | Week trailer count validation (0 to AllowedPerWeek) | Manual process | Not started
Test data preparation | CSV Generator – Yearly | CSV_GEN_Y05 | ISO year with 52 vs 53 weeks | Manual process | Not started
Test data preparation | CSV Generator – Yearly | CSV_GEN_Y06 | Export yearly nomination CSV (happy path) | Manual process | Not started
Test data preparation | CSV Generator – Yearly | CSV_GEN_Y07 | Export blocked when template not generated | Manual process | Not started
Test data preparation | CSV Generator – Yearly | CSV_GEN_Y08 | Export blocked when a month cell is empty | Manual process | Not started
Test data preparation | CSV Generator – Yearly | CSV_GEN_Y09 | Export blocked when a week cell is empty | Manual process | Not started
Test data preparation | CSV Generator – Yearly | CSV_GEN_Y10 | Export blocked when month value exceeds AllowedPerMonth | Manual process | Not started
Test data preparation | CSV Generator – Yearly | CSV_GEN_Y11 | Export blocked when week value exceeds AllowedPerWeek | Manual process | Not started
Test data preparation | CSV Generator – Yearly | CSV_GEN_Y12 | Invalid ConfigYear rejected on template build | Manual process | Not started
Test data preparation | CSV Generator – Yearly | CSV_GEN_Y13 | Build realistic yearly file for both offtakers | Manual process | Not started